## Meilensteine
Gantt-Diagramm zur Implementierung |  |  | Woche | 28 |  | 29 |  |  | 30 |  |  | 31 |  |  | 32
|  |  | Arbeitsschritte | Aufsetzen der Entwicklungs-Umgebung | MS 1: Initialisierung/ Prototypenfeld |  | Puffer | MS 2: MeasurementConfiguration aufbauen |  | Puffer | MS 3: Messlauf starten |  | Puffer | MS 4: Laden und Speichern + Usability |  | Puffer
Modul |  |  | Veratnwortung
Submodul
Klasse
Controller
Model Interface
|  | IModelInformation | [14 empty] | Legende
|  | IMeasurementRun | [14 empty] | David
| View Controller Interface | [15 empty] | Linus
|  | ButtonAction | [14 empty] | Jan
|  | BlockAction | [14 empty] | Stefan
|  | ConnectionAction | [14 empty] | Leon
Command Pattern
|  | CommandManager | [14 empty] | Bei Beginn einer Bearbeitung soll der Name des Bearbeitendes über das schwarze Feld der Klasse eingetragen werden. Dies dient als Zeichen dafür, dass andere Teammitglieder diese Klasse nicht bearbeiten sollten.
Command
AddBlockToConfigCommand
ModifyBlockInConfigCommand
RemoveBlockFromConfigCommand
EditBlockPropertiesCommand
CloneBlockCommand
ExportBlockPrototypeCommand
SaveConfigCommand
LoadConfigCommand
ResetConfigCommand
CreateChannelConnectionCommand
ModifyChannelConnectionCommand
DeleteChannelConnectionCommand
StartRunCommand
StopRunCommand
ResumeRunCommand
FileService
Services
|  | YamlService |  |  |  | Linus 100&+ Test 100% | [7 empty] | Linus 100%+ Test 100%
|  | CsvService | [12 empty] | lLinus 100%+ Test 100%
|  | PngService | [12 empty] | Llinus 100%+ Test 100%
GUI
|  | MainWindow |  |  | Linus- vorläufige GUI für unsere Anwendung -ca. 80%
Menues
|  | PrototypeField |  |  | Leon - Stubs integriert und Interfaces implementiert
|  | SensorBlockField |  |  | Leon - Stubs integriert und Interfaces implementiert
|  | TransformationBlockField |  |  |  | Leon
|  | RepresentationBlockField |  |  |  | Leon
FieldHandler
Configuration
|  | ConfigurationField | [5 empty] | Linus- Konfigurationsfeld wurde durch den Editor ersetzt ca. 50%
|  | BlockDragAndDropHandler | [5 empty] | Leon
|  | BuildingBlockView | [5 empty] | Leon
|  | SensorBlockView | [5 empty] | Leon
|  | TransformationBlockView | [5 empty] | Leon
|  | RepresentationBlockView | [5 empty] | Leon
|  | HelpDecoratorHandler | [5 empty] | Leon
AddWireDragAndDropHandler
RemoveWireDragAndDropHandler
ChannelDecorator
OutChannelDecorator
InChannelDecorator
Wire
Building Block Properties
|  | BuildingBlockProperties | [5 empty] | Leon
|  | BuildingBlockPropertiesHandler | [5 empty] | Leon
|  | SensorBlockProperties | [5 empty] | Leon
TransformationBlockProperties
TransBlockPropertiesHandler
RepresentationBlockProperties
ReprBlockPropertiesHandler
Button
|  | Button |  |  | Linus -inbegiffen in ButtonField - ca 80%
|  | ButtonHandler |  | Linus - inbegriffen in ButtonField -ca. 80%
Exception
|  | ExceptionWindowManager |  |  | Linus -90%
|  | ExceptionWindow |  |  | Linus -90%
|  | BuildingBlockExceptionWindow | [5 empty] | Linus -90%
|  | ConnectionExceptionWindow | [6 empty] | Linus -90%
|  | GeneralExceptionWindow |  |  | Linus -90%
HelpAndOption
OptionsWindow
HelpWindow
HelpWindowHandler
OptionsWindowHandler
FacadeControllerView
|  | PickUpPointControllerView | [5 empty] | Leon
|  | IButtonAction |  | Linus -100 % Fassade erstmal reduziert auf elementare Aktionen
IBlockAction
IConnectionAction
FacadeModelView
ViewDirectoryInterface
Model
Core
MeasurementRun
MesurementRunState
MeasurementConfiguration
BuildingBlock
HelpMessage
|  | YamlRepresentation |  |  |  | David
|  | BuildingBlockDirectory |  |  |  | David
Transformation Logic
Function
Transformation
Representation Logic
Representation
TableRespresentation
XYRepresentation
Sensor Logic
Sensor
PhysicalSensor
VirtualSensor
Channel Logic
Channel
ChannelState
Connected
UnConnected
ValueReady
InChannel
OutChannel
Building Block Builder
|  | Director |  |  |  | David
|  | Builder |  |  |  | David
|  | SnakeYamlParser |  |  |  | David
|  | SensorBuilder |  |  |  | David
PhysicalSensorBuilder
VirtualSensorBuilder
|  | TransformationBuilder |  |  |  | David
|  | RepresentationBuilder |  |  |  | David
XYRepresentationBuilder
TableRepresentationBuilder
Façades
PickUpPointViewFacades
UpdateInterface
GraphicDataIolnterface
ExceptionInterface
MeasurementDataInterface
MRunReaction
MRunInfo
ModelManager
Backend
Measurement Logic
IAccessToSensorInfo
IAccessToMRun
MeasurementState
MRunAgent
SensorInfoAgent
PickPointForAgentsBasedOnSsh
InitDataForSsh
IMStreamListener
Command Factory
ComToPi
SshToPi
CommandFactory
SshCommandFactory
CommandGetSensorIds
SshCommandGetSensorIds
CommandCopyFromPi
SshCommandCopyFromPi
CommandCopyToPi
SshCommandCopyToPi
CommandMRunAtPi
SshCommandMRunAtPi
SystemProcessCommandLine
BufferedReader
Writer
MRunThread
Thread
Runnable
Cache
Cache Logic
MRunTiming
Timer
Cache
BufferForOneSensorInChannel
TimestampValuePair
ConnectionTerminatedAction
TimeoutAction
ErrorCodeAction
DataSetCompleteAction
EnhancedValuePacket
ErrorCodesForInChannel
CheckAndNotifyAction
IMRunListener
IMRunInfo
TimerTask

## Implementierungsplan
|  |  | Woche | 27 | 28 | [6 empty] | 29 | [6 empty] | 30 | [6 empty] | 31 | [6 empty] | 32
|  |  | Tag | 2019-07-07 | 2019-07-08 | 2019-07-09 | 2019-07-10 | 2019-07-11 | 2019-07-12 | 2019-07-13 | 2019-07-14 | 2019-07-15 | 2019-07-16 | 2019-07-17 | 2019-07-18 | 2019-07-19 | 2019-07-20 | 2019-07-21 | 2019-07-22 | 2019-07-23 | 2019-07-24 | 2019-07-25 | 2019-07-26 | 2019-07-27 | 2019-07-28 | 2019-07-29 | 2019-07-30 | 2019-07-31 | 2019-08-01 | 2019-08-02 | 2019-08-03 | 2019-08-04 | 2019-08-05 | 2019-08-06 | 2019-08-07 | 2019-08-08 | 2019-08-09 | 2019-08-10 | 2019-08-11
Modul
Submodul
|  | Klasse | Verantwortung
Controller |  |  | Jan
Model Interface
IModelInformation
IMeasurementRun
View Controller Interface
ButtonAction
BlockAction
ConnectionAction
Command Pattern
CommandManager
Command
AddBlockToConfigCommand
ModifyBlockInConfigCommand
RemoveBlockFromConfigCommand
EditBlockPropertiesCommand
CloneBlockCommand
ExportBlockPrototypeCommand
SaveConfigCommand
LoadConfigCommand
ResetConfigCommand
CreateChannelConnectionCommand
ModifyChannelConnectionCommand
DeleteChannelConnectionCommand
StartRunCommand
StopRunCommand
ResumeRunCommand
FileService |  |  | Jan
Services
YamlService
CsvService
PngService
GUI |  |  | Linus
MainWindow
Menues
PrototypeField
TransformationBlockField
RepresentationBlockField
FieldHandler
Configuration
ConfigurationField
BlockDragAndDropHandler
BuildingBlockView
SensorBlockView
TransformationBlockView
RepresentationBlockView
HelpDecoratorHandler
AddWireDragAndDropHandler
RemoveWireDragAndDropHandler
ChannelDecorator
OutChannelDecorator
InChannelDecorator
Wire
Building Block Properties
BuildingBlockProperties
BuildingBlockPropertiesHandler
SensorBlockProperties
TransformationBlockProperties
TransBlockPropertiesHandler
RepresentationBlockProperties
ReprBlockPropertiesHandler
Button
Button
ButtonHandler
Exception
ExceptionWindowManager
ExceptionWindow
BuildingBlockExceptionWindow
ConnectionExceptionWindow
GeneralExceptionWindow
HelpAndOption
OptionsWindow
HelpWindow
HelpWindowHandler
OptionsWindowHandler
FacadeControllerView
PickUpPointControllerView
IButtonAction
IBlockAction
IConnectionAction
FacadeModelView
ViewDirectoryInterface
Model |  |  | David/Leon
Core
MeasurementRun
MesurementRunState
MeasurementConfiguration
BuildingBlock
HelpMessage
YamlRepresentation
BuildingBlockDirectory
Transformation Logic
Function
Transformation
Representation Logic
Representation
TableRespresentation
XYRepresentation
Sensor Logic
Sensor
PhysicalSensor
VirtualSensor
Channel Logic
Channel
ChannelState
Connected
UnConnected
ValueReady
InChannel
OutChannel
Building Block Builder
Director
Builder
SnakeYamlParser
SensorBuilder
PhysicalSensorBuilder
VirtualSensorBuilder
TransformationBuilder
RepresentationBuilder
XYRepresentationBuilder
TableRepresentationBuilder
Façade Controller View
PickUpPointViewFacades
UpdateInterface
GraphicDataIolnterface
ExceptionInterface
MeasurementDataInterface
MRunReaction
MRunInfo
ModelManager
Backend |  |  | Stefan
Measurement Logic
IAccessToSensorInfo
IAccessToMRun
MeasurementState
MRunAgent
SensorInfoAgent
PickPointForAgentsBasedOnSsh
InitDataForSsh
IMStreamListener
Command Factory
ComToPi
SshToPi
CommandFactory
SshCommandFactory
CommandGetSensorIds
SshCommandGetSensorIds
CommandCopyFromPi
SshCommandCopyFromPi
CommandCopyToPi
SshCommandCopyToPi
CommandMRunAtPi
SshCommandMRunAtPi
SystemProcessCommandLine
BufferedReader
Writer
MRunThread
Thread
Runnable
Cache |  |  | Stefan
Cache Logic
MRunTiming
Timer
Cache
BufferForOneSensorInChannel
TimestampValuePair
ConnectionTerminatedAction
TimeoutAction
ErrorCodeAction
DataSetCompleteAction
EnhancedValuePacket
ErrorCodesForInChannel
CheckAndNotifyAction
IMRunListener
IMRunInfo
TimerTask