## Meilensteine
Gantt-Diagramm zur Implementierung			Woche	28		29			30			31			32
			Arbeitsschritte	Aufsetzen der Entwicklungs-Umgebung	MS 1: Initialisierung/ / PrototypenfeldMS 1: Initialisierung/ / PrototypenfeldMS 1: Initialisierung/ / PrototypenfeldMS 1: Initialisierung/ / PrototypenfeldMS 1: Initialisierung/ / PrototypenfeldMS 1: Initialisierung/ / PrototypenfeldMS 1: Initialisierung/ / PrototypenfeldMS 1: Initialisierung/ / PrototypenfeldMS 1: Initialisierung/ / PrototypenfeldMS 1: Initialisierung/ / PrototypenfeldMS 1: Initialisierung/ / PrototypenfeldMS 1: Initialisierung/ / Prototypenfeld		Puffer	MS 2: MeasurementConfiguration aufbauen		Puffer	MS 3: Messlauf starten		Puffer	MS 4: Laden und Speichern + Usability		Puffer
Modul			Veratnwortung
	Submodul
		Klasse
Controller
	Model Interface
		IModelInformation																	Legende
		IMeasurementRun																	David
	View Controller Interface																		Linus
		ButtonAction																	Jan
		BlockAction																	Stefan
		ConnectionAction																	Leon
	Command Pattern
		CommandManager																	Bei Beginn einer Bearbeitung soll der Name des Bearbeitendes über das schwarze Feld der Klasse eingetragen werden. Dies dient als Zeichen dafür, dass andere Teammitglieder diese Klasse nicht bearbeiten sollten.
		Command
		AddBlockToConfigCommand
		ModifyBlockInConfigCommand
		RemoveBlockFromConfigCommand
		EditBlockPropertiesCommand
		CloneBlockCommand
		ExportBlockPrototypeCommand
		SaveConfigCommand
		LoadConfigCommand
		ResetConfigCommand
		CreateChannelConnectionCommand
		ModifyChannelConnectionCommand
		DeleteChannelConnectionCommand
		StartRunCommand
		StopRunCommand
		ResumeRunCommand
FileService
	Services
		YamlService
		CsvService
		PngService
GUI
		MainWindow
	Menues
		PrototypeField
		SensorBlockField
		TransformationBlockField
		RepresentationBlockField
		FieldHandler
	Configuration
		ConfigurationField						Leon
		BlockDragAndDropHandler						Leon
		BuildingBlockView						Leon
		SensorBlockView						Leon
		TransformationBlockView						Leon
		RepresentationBlockView						Leon
		HelpDecoratorHandler						Leon
		AddWireDragAndDropHandler
		RemoveWireDragAndDropHandler
		ChannelDecorator
		OutChannelDecorator
		InChannelDecorator
		Wire
	Building Block Properties
		BuildingBlockProperties						Leon
		BuildingBlockPropertiesHandler						Leon
		SensorBlockProperties						Leon
		TransformationBlockProperties
		TransBlockPropertiesHandler
		RepresentationBlockProperties
		ReprBlockPropertiesHandler
	Button
		Button
		ButtonHandler
	Exception
		ExceptionWindowManager
		ExceptionWindow
		BuildingBlockExceptionWindow						Leon
		ConnectionExceptionWindow
		GeneralExceptionWindow
	HelpAndOption
		OptionsWindow
		HelpWindow
		HelpWindowHandler
		OptionsWindowHandler
	FacadeControllerView
		PickUpPointControllerView						Leon
		IButtonAction
		IBlockAction
		IConnectionAction
	FacadeModelView
		ViewDirectoryInterface
Model
	Core
		MeasurementRun
		MesurementRunState
		MeasurementConfiguration
		BuildingBlock
		HelpMessage
		YamlRepresentation				David
		BuildingBlockDirectory				David
	Transformation Logic
		Function
		Transformation
	Representation Logic
		Representation
		TableRespresentation
		XYRepresentation
	Sensor Logic
		Sensor
		PhysicalSensor
		VirtualSensor
	Channel Logic
		Channel
		ChannelState
		Connected
		UnConnected
		ValueReady
		InChannel
		OutChannel
	Building Block Builder
		Director				David
		Builder				David
		SnakeYamlParser				David
		SensorBuilder				David
		PhysicalSensorBuilder
		VirtualSensorBuilder
		TransformationBuilder				David
		RepresentationBuilder				David
		XYRepresentationBuilder
		TableRepresentationBuilder
	Façade
		PickUpPointViewFacades
		UpdateInterface
		GraphicDataIolnterface
		ExceptionInterface
		MeasurementDataInterface
		MRunReaction
		MRunInfo
		ModelManager
Backend
	Measurement Logic
		IAccessToSensorInfo
		IAccessToMRun
		MeasurementState
		MRunAgent
		SensorInfoAgent
		PickPointForAgentsBasedOnSsh
		InitDataForSsh
		IMStreamListener
	Command Factory
		ComToPi
		SshToPi
		CommandFactory
		SshCommandFactory
		CommandGetSensorIds
		SshCommandGetSensorIds
		CommandCopyFromPi
		SshCommandCopyFromPi
		CommandCopyToPi
		SshCommandCopyToPi
		CommandMRunAtPi
		SshCommandMRunAtPi
		SystemProcessCommandLine
		BufferedReader
		Writer
		MRunThread
		Thread
		Runnable
Cache
	Cache Logic
		MRunTiming
		Timer
		Cache
		BufferForOneSensorInChannel
		TimestampValuePair
		ConnectionTerminatedAction
		TimeoutAction
		ErrorCodeAction
		DataSetCompleteAction
		EnhancedValuePacket
		ErrorCodesForInChannel
		CheckAndNotifyAction
		IMRunListener
		IMRunInfo
		TimerTask

## Implementierungsplan
			Woche	27	28					29					30					31					32
			Tag	07. Jul	08. Jul	09. Jul	10. Jul	11. Jul	12. Jul	13. Jul	14. Jul	15. Jul	16. Jul	17. Jul	18. Jul	19. Jul	20. Jul	21. Jul	22. Jul	23. Jul	24. Jul	25. Jul	26. Jul	27. Jul	28. Jul	29. Jul	30. Jul	31. Jul	01. Aug	02. Aug	03. Aug	04. Aug	05. Aug	06. Aug	07. Aug	08. Aug	09. Aug	10. Aug	11. Aug
Modul
	Submodul
		Klasse	Verantwortung
Controller			Jan
	Model Interface
		IModelInformation
		IMeasurementRun
	View Controller Interface
		ButtonAction
		BlockAction
		ConnectionAction
	Command Pattern
		CommandManager
		Command
		AddBlockToConfigCommand
		ModifyBlockInConfigCommand
		RemoveBlockFromConfigCommand
		EditBlockPropertiesCommand
		CloneBlockCommand
		ExportBlockPrototypeCommand
		SaveConfigCommand
		LoadConfigCommand
		ResetConfigCommand
		CreateChannelConnectionCommand
		ModifyChannelConnectionCommand
		DeleteChannelConnectionCommand
		StartRunCommand
		StopRunCommand
		ResumeRunCommand
FileService			Jan
	Services
		YamlService
		CsvService
		PngService
GUI			Linus
		MainWindow
	Menues
		PrototypeField
		TransformationBlockField
		RepresentationBlockField
		FieldHandler
	Configuration
		ConfigurationField
		BlockDragAndDropHandler
		BuildingBlockView
		SensorBlockView
		TransformationBlockView
		RepresentationBlockView
		HelpDecoratorHandler
		AddWireDragAndDropHandler
		RemoveWireDragAndDropHandler
		ChannelDecorator
		OutChannelDecorator
		InChannelDecorator
		Wire
	Building Block Properties
		BuildingBlockProperties
		BuildingBlockPropertiesHandler
		SensorBlockProperties
		TransformationBlockProperties
		TransBlockPropertiesHandler
		RepresentationBlockProperties
		ReprBlockPropertiesHandler
	Button
		Button
		ButtonHandler
	Exception
		ExceptionWindowManager
		ExceptionWindow
		BuildingBlockExceptionWindow
		ConnectionExceptionWindow
		GeneralExceptionWindow
	HelpAndOption
		OptionsWindow
		HelpWindow
		HelpWindowHandler
		OptionsWindowHandler
	FacadeControllerView
		PickUpPointControllerView
		IButtonAction
		IBlockAction
		IConnectionAction
	FacadeModelView
		ViewDirectoryInterface
Model			David/Leon
	Core
		MeasurementRun
		MesurementRunState
		MeasurementConfiguration
		BuildingBlock
		HelpMessage
		YamlRepresentation
		BuildingBlockDirectory
	Transformation Logic
		Function
		Transformation
	Representation Logic
		Representation
		TableRespresentation
		XYRepresentation
	Sensor Logic
		Sensor
		PhysicalSensor
		VirtualSensor
	Channel Logic
		Channel
		ChannelState
		Connected
		UnConnected
		ValueReady
		InChannel
		OutChannel
	Building Block Builder
		Director
		Builder
		SnakeYamlParser
		SensorBuilder
		PhysicalSensorBuilder
		VirtualSensorBuilder
		TransformationBuilder
		RepresentationBuilder
		XYRepresentationBuilder
		TableRepresentationBuilder
	Façade Controller View
		PickUpPointViewFacades
		UpdateInterface
		GraphicDataIolnterface
		ExceptionInterface
		MeasurementDataInterface
		MRunReaction
		MRunInfo
		ModelManager
Backend			Stefan
	Measurement Logic
		IAccessToSensorInfo
		IAccessToMRun
		MeasurementState
		MRunAgent
		SensorInfoAgent
		PickPointForAgentsBasedOnSsh
		InitDataForSsh
		IMStreamListener
	Command Factory
		ComToPi
		SshToPi
		CommandFactory
		SshCommandFactory
		CommandGetSensorIds
		SshCommandGetSensorIds
		CommandCopyFromPi
		SshCommandCopyFromPi
		CommandCopyToPi
		SshCommandCopyToPi
		CommandMRunAtPi
		SshCommandMRunAtPi
		SystemProcessCommandLine
		BufferedReader
		Writer
		MRunThread
		Thread
		Runnable
Cache			Stefan
	Cache Logic
		MRunTiming
		Timer
		Cache
		BufferForOneSensorInChannel
		TimestampValuePair
		ConnectionTerminatedAction
		TimeoutAction
		ErrorCodeAction
		DataSetCompleteAction
		EnhancedValuePacket
		ErrorCodesForInChannel
		CheckAndNotifyAction
		IMRunListener
		IMRunInfo
		TimerTask